## Changes & Requirements
WBM Changes and New Requirements
First Report : 2015-05-22
Last Update: 2015-05-22
# | Recorded Date | Module | Description | Type | Demo on Friday | Responsible | Status | Uploaded Status | Priority | Notes/Remarks
1 | 2015-05-22 | Initiative Management | Under Activity Tab - Add Resource Type: Staff, Machine, Materials | Change Request | Yes | George | Completed |  | 1
2 | 2015-05-22 | Initiative Management | Expense Budget and benefits add Plan Budget, Actual Budget; | Change Request | Yes | Nivas | Completed |  | 1
3 | 2015-05-22 | Issue Management | Under issue type add type: Expense Budget Deviation; Benefits budget deviation. Bug Fix/Misunderstanding/Logic Modification/Business Rule Addition/New Requirement/New Idea. Use all types from JIRA | New Requirement | Yes | Stephen | Completed |  | 1
4 | 2015-05-22 | Initiative Management | Under initiative add Activity type of payment gate. default to % but override | Change Request | No |  |  |  | 1
5 | 2015-05-21 | Issue Management | Hierarchy of the modules should be : Initiative ---Activity -----Task -------To Do Issues, Colloborative Notes, Attachements, Messages and Chat at all level. | Change Request | No | Stephen | Completed |  | 1
6 | 2015-05-21 | Initiative Management | Rename "Issues" to "Requirements/Issues" under the Initiative Menu item | Change Request | Yes | George | Completed |  | 1
7 | 2015-05-21 | Initiative Management | Move "Issue Configuration" to Configuration Menu | Change Request | Yes | George | Completed |  | 1
8 | 2015-05-21 | Initiative Management | Rename "Resources and Applications" to "Applications" | Change Request | Yes | George | Completed |  | 1
9 | 2015-05-21 | Initiative Management | User Manual should have html link (TOC, Endnote, Footnote) | Change Request | No |  |  |  | 2
10 | 2015-05-21 | Initiative Management | Link "Report a problem" to Issue | Change Request | Yes | George | Completed |  | 1
11 | 2015-05-21 | Initiative Management | User Groups are : Admin Executive Project Leader Project Support Team Members Power User (Overriding Capability) Corporate Content Manager (Can update only contents of Corporate Portal) Department Content Manager(Can update only contents of Department Portal) Follower (View all issues/initiatives) | Change Request | No | George |  |  | 2
12 | 2015-05-21 | Initiative Management | The User Role for each user group to be defined | Change Request | No |  |  |  | 1
13 | 2015-05-21 | Initiative Management | Automatically Add the proposer of the initiative using login credentials. | Change Request | Yes | Susai | Completed |  | 1
14 | 2015-05-21 | Initiative Management | Remove "Caution" from Initiative Proposal Screen | Change Request | Yes | Susai | Completed |  | 1
15 | 2015-05-21 | Initiative Management | Status of Initiative -- (Approved, Need Further Research, Declined Reason) | Change Request | Yes | George | Completed |  | 1
16 | 2015-05-21 | Initiative Management | Step 1: Propose Initiatives and Approve Initiatives Step 2: All approved initiatives will be ready for resource allocation, adding activites etc., | Change Request | Yes | Nivas | Completed |  | 1
17 | 2015-05-21 | Initiative Management | Tabs will be --Questions & Answers --Budget --Benefits --Supporting Documents | Change Request | Yes | Nivas/George | Completed |  | 1
18 | 2015-05-21 | Issue Management | Remove Epic Link in Add/Edit Screen of Issue Management | New Requirement | Yes | Stephen | Completed |  | 1
19 | 2015-05-21 | Issue Management | Linking an Issue to a Features or Requirements (optional) | New Requirement | No | Stephen |  |  | 1
20 | 2015-05-21 | Issue Management | List Issues 2/4 (2 is new and 4 is total ) on the home page of initiative. | New Requirement | yes | Stephen | completed |  | 1
21 | 2015-05-21 | Issue Management | Project leader or Power user can change the status of Issues | New Requirement | Yes | Stephen/Susai | Inprogress |  | 1
22 | 2015-05-21 | Issue Management | Email notifications for new issues, Change in status. | New Requirement | Yes | Stephen | Completed |  | 1
23 | 2015-05-21 | Issue Management | Manage Hours for each issues. If Issues is (New Requirement / Deviation > 15%) use it for billing or just leave the hrs as it is. | New Requirement | No | Stephen | Open |  | 1
24 | 2015-05-21 | Issue Management | Project Lead will have access to all issues | New Requirement | Yes | Susai | Inprogress |  | 1
25 | 2015-05-21 | Issue Management | Executive can view all issues across initiatives | New Requirement | yes | Stephen | completed |  | 1
26 | 2015-05-21 | Issue Management | Members can view/contribute to issues assigned/unassigned to them. | New Requirement | Yes | Stephen | Open |  | 1
27 | 2015-05-21 | Issue Management | Assigning Followers for Issues. Attaching docs as well. | New Requirement | Yes | Susai | Completed |  | 1
28 | 2015-05-21 | Initiative Management | There will be 3 types of portal: --Corporate Portal ---- Bring Reports in Corporate Portal --Initiative Portal (Have same items of Corporate Portal) --Department Portal | Change Request | Yes | George | Completed |  | 1
29 | 2015-05-21 | Document Management | Integrating Alfresco with Odoo | Change Request | No |  |  |  | 1
30 | 2015-05-22 | Initiative Management | Load Timesheet, Invoice/payables and Contract module | Phase 2 |  |  |  |  | 4
31 | 2015-05-22 | Initiative Management | Each initiative will have payment milestones | Phase 2 |  |  |  |  | 4
32 | 2015-05-22 | Initiative Management | There willl be contract for each Initiative which references payment milestones and deliverables. | Phase 2 |  |  |  |  | 4
33 | 2015-05-21 | Issue Management | Screen Capture and directly link it to the issue (like JIRA) | Research |  | Stephen | Open |  | 3
34 | 2015-05-21 | Issue Management | Each Issue can be assigned to Module, Requirement to the Issue, Issue Date, When acknowledged, approved, signed-off internally and signed-off externally. | New Requirement | No | Stephen | Open |  | 2
35 | 2015-05-21 | Issue Management | Managing Version for the Issues | New Requirement | Yes | Stephen | Completed |  | 2
36 | 2015-05-21 | Issue Management | Mappying JIRA to Customized Issue Management : EPIC - Capability/Functionality (Removed) Story -- Requirement Tasks -- Detailed Specifications | New Requirement | No | Stephen | Open |  | 2
37 | 2015-05-21 | Issue Management | Jira, Tempo Folio, Tempo Planner, Tempo Timesheets? jira xray,jira gant chart, arsenale dataplane reporting? create on transition? big picture plugin? jira mobility for phone and tablet | Research |  | Stephen |  |  | 2
38 | 2015-05-22 | Portal | Onboard portal for each recruit; examples of their documents; send tax info to irs edi(not in demo); output benefits in spreadsheet, pdf or XML to benefits providor. Portal for for benefits providers. employees have ability to change hr data later with notifications reminding them and approval of changes. | Research |  |  |  |  | 3
39 | 2015-05-22 | HR | Vacation request module | POC | Yes | Sathish | Completed |  | 3
40 | 2015-05-22 | Issue Management | Build vs integrate jira..jira not as expensive as thought with server option… (https://www.atlassian.com/software/jira/pricing/?tab=server ) and for App: https://apps.openerp.com/apps/modules/7.0/idea/ and https://apps.openerp.com/apps/modules/6.1/project_ppm/ | RESEARCH |  | George |  |  | 2
41 | 2015-05-22 | Survey | Survey Tool : use this for questions section of proposed initiative. that way we have flexibility. Also we can see if some way to score responses ato prioritize initiatives. Add survey function to CRM, to have standard qualification questions. | POC | No |  |  |  | 3
42 | 2015-05-22 | CRM | Link initiative tool to CRM Hub. Each opportunity is an initiative. In that way we can have standard activities, tasks, to dos, issues, and track changes in requirements for quote just like we do for software. for various types of leads, and provide all collaboration and follow up tools available in sales process? | Research |  |  |  |  | 3
43 | 2015-05-22 | Forum | Forum Module for FAQ | Research |  |  |  |  | 3
44 | 2015-05-22 | Events | Use Events or Advanced Event Modules for to manage Onboarding and training sessions, Company Events, Volunteer Event, Golf Event | Research |  |  |  |  | 3
45 | 2015-05-22 | Vehicle Fleet | Vehicle Fleet Log : To Manage the Fleet | Research |  |  |  |  | 3
46 | 2015-05-22 | Lunch Orders | Lunch Orders : To manage lunch orders such as procuring sandwiches, pizzas and other, from usual suppliers, for their employees to offer them more facilities. | Research |  |  |  |  | 3
47 | 2015-05-22 | Issue Management | Project Lead can assign. Anyone can create the issue | New Requirement | No | Stephen | Open |  | 1
48 | 2015-05-26 | Liferay | Liferay Menu navigation consistency, User access and Setup odoo pages | Change Request | Yes | Daniel | completed
49 | 2015-05-21 | CRM | Crm, lead and opportunities module to replace hub module | New Requirement | Yes | Xavier, Prabhu | Inprogress
50 | 2015-05-27 | Issue Management | Issue management with voice recording | New Requirement | Yes | Vivek, Moses | Completed
51 | 2015-05-21 | HR | Install all HR related modules | New Requirement | Yes | Nivas | Inprogress
52 | 2015-05-26 | Project | Study about project managmt capabilities in odoo. | Research |  | Muthu
53 | 2015-05-26 | Project | Add notes tab in initiative proposal | Change Request | Yes | George | Completed
54 | 2015-05-26 | Project | Reason type for Declined reason | Change Request | Yes | George | Completed
55 | 2015-05-26 | Project | Quote&Contract in Initiative and show when initiative is approved | Change Request | Yes | George | Completed |  | 1
56 | 2015-05-26 | Project | Create Financial tab(Fields All payments made, need to be made) in Initiative proposal | Change Request | Yes | George | Completed
57 | 2015-05-26 | Project | Executive only approves the initiative proposal | New Requirement | Yes | George | Completed
58 | 2015-05-26 | Project | Rename Stage to Status and Move status(new, In progress and Completed) on top in Activity. Remove Approval Status, Budget and Actual | Change Request | Yes | George | Completed
59 | 2015-05-26 | Project | Remove responsible users in activity and add assign to field | Change Request | Yes | George | Completed
60 | 2015-05-26 | Project | Add key deliverable tab and it should be multiple(Test box or Documents) | New Requirement | Yes | George | Completed
61 | 2015-05-26 | Project | Add expense type in initiative | New Requirement | Yes | George | Completed
62 | 2015-05-26 | Issue Management | Add issue type based on Billable, Non billable and Associate change request module | New Requirement | Yes | Stephen | Completed
63 | 2015-05-26 | Issue Management | Create field for screen shot | New Requirement | yes | Stephen | Completed
64 | 2015-05-26 | Issue Management | Issue stages (Identified, Acknowledged, Analysis, Solution, Development, Internal Sign off, Client Sign off, Production) | New Requirement | Yes | Stephen | Completed
65 | 2015-05-26 | Issue Management | Add agreed date of delivery approved hours and approved dollars | New Requirement | Yes | George | Completed
66 | 2015-05-26 | Issue Management | Issue kanban view Unscheduled, Today, this week, next two weeks, Next month, Beyond month. | New Requirement | Yes | George | Completed
67 |  |  | Create Access to finance filed and show financial data based on it | New Requirement | Yes | George | Completed |  | 1
68 |  |  | Executive will have access to finance tab in initiative | New Requirement | Yes | George | Completed
69 |  |  | Add tags in Initiative, Activity, TODO,Issue Management, Notes | New Requirement | Yes | George | Completed
70 |  |  | Create customers and vendors fields in initiative | New Requirement | Yes | Stephen | Completed
71 |  |  | Create user matrix | Change Request | Yes | Xavier | Inprogress
72 |  |  | Enable email access in staging | New Requirement | Yes | Daniel | Completed
73 |  |  | Setup sample data and remove existing | New Requirement | Yes | Daniel | Completed
74 |  |  | Update liferay menu structure | Change Request | Yes | Xavier,Vincent | Completed |  | 1
75 |  |  | Put Issues in the Corporate Portal under Messages | Change Request | Yes | Xavier | Completed
76 |  |  | Width of sub menu items to be fixed across all menu items. | Change Request | Yes | Susai | Completed
77 |  |  | Add "Resources" under "Resources and Reports" below "Directories" | Change Request | Yes | Xavier | Completed
78 |  |  | Use Document Management available Odoo. | Change Request | Yes | Sathish | Completed
79 |  |  | Research on collaborating with Alfresco, LifeRay and Odoo. | Research | No | Sathish
80 |  |  | Bring "Initiatives" as separate menu item in CP and it should appear after logging in. | Change Request | Yes | Xavier | Completed
81 |  |  | Remove "Applications" from Initiatives | Change Request | Yes | Xavier | Completed
82 |  |  | Put "To Do" above Issues in "Initiatives" menu item | Change Request | Yes | Xavier | Completed
83 |  |  | Reduce the width of the left widgets to accommodate the calender feature. | Change Request |  | Susai | Completed
84 |  |  | Roles -- Power User has all rights of Team member + Additional Rights (Yet to decide)
85 |  |  | Questions will be preloaded for the initiatives. It will come in Configuration Menu. (Not for 3rd June Demo) | New Requirement | No | George | Completed
86 |  |  | Executive will post 4 questions to each initiative at random. He can take it back at any point if it not answered. If answered he cannot take back the question. (Not for 3rd June Demo) | Change Request | No | George | Completed
87 |  |  | Proposer will post the answers for the questions posted to him. (Not for 3rd June Demo) | New Requirement | No | Geroge | Completed
88 |  |  | Supporting Documents can be URL and also attach documents. Multiple documents can be uploaded. (Wireframes, Process Maps can be attached) | Change Request | Yes | George | Completed
89 |  |  | Notes should allow collaboration with slider bar with different colors. (Not for 3rd June Demo) | New Requirement | No | George | Completed
90 |  |  | Remove "Attachments" which appears next to "More" on the status bar on top. | Change Request |  | Stephen
91 |  |  | Automatically take an initiative once the executive approves it. No more approval at Management level. | Change Request | Yes | George | Completed
92 |  |  | Add Sub-initiatives to Initiatives (Parent and Child Initiative). A Text field alone. | Change Request | Yes | Susai | Completed
93 |  |  | List Parent Initiatives related to a department. | Change Request | No | George
94 |  |  | % of Completion can be broken among different stages. | Change Request |  | Nivas
95 |  |  | Put "Status" (Open, In-progress, Complete) | Change Request |  | Nivas
96 |  |  | Stages will be "POC, Design, Development, Testing, etc.,) | Change Request |  | Nivas
97 |  |  | Add "Notes" tab to Activity, next to "Documents". | New Requirement | Yes | Nivas | Completed
98 |  |  | Each Activity can have different stages. This can be configured in the Activity Template (Not for 3rd June Demo) | New Requirement | No | George
99 |  |  | Change "Type" on Activities to "Activity Reference". | Change Request | Yes | Susai | Completed
100 |  |  | Put Activity Type separately. (Configurable) | Change Request | Yes | Susai | Completed
101 |  |  | Sorting Order for the Kanban View of the initiatives. Right now first entered comes on top. (Not for 3rd June Demo) | Change Request | No | Susai
102 |  |  | Sorting Order for Gantt Chart View.(Not for 3rd June Demo) Need Research. | Change Request | No | George
103 |  |  | Gantt Chart/Kanban View for all the activities, within the initiative for a particular department. It can see in weeks. (Reference: MS Project) (Not for 3rd June Demo) | Change Request | No | George

## User roles
Customer Role
Vendor Team Member
Vendor Project Manager
Vendor Engagement Executive
Financial Role

## Expenses & Benefits
Expenses Budget
# | MONTHS | Planned | Actual | Difference
Month #1
Month #2
Month #3
Month #4
Month #5
Month #6
Total
Benefits Budget
# | Months | Planned | Actual | Difference
Month #1
Month #2
Month #3
Month #4
Month #5
Month #6
Total

## Sheet3
Budget
# | MONTHS | Resource | Budget
Month #1
Month #2
Month #3
Month #4
Month #5
Month #6
Total

## Support Docs
Support Document Uploading
# | Title | Date Uploaded | Uploaded by | URL